## Gantt Chart
GANTT CHART CPE-414
PROJECT TITLE |  | smart traffic light system |  |  |  |  | COMPANY NAME | [6 empty] | BS
PROJECT MANAGER |  | Rathanon |  |  |  |  | DATE | [6 empty] | 2026-01-16
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Preparation
1.1 | Project requirment | Rathanon | 2026-01-16 | 2026-01-16 | 0 | 100% | bar: WEEK 1 F
1.1.1 | Project Chart | Tanakorn | 2026-01-16 | 2026-01-16 | 0 | 100% | bar: WEEK 1 F
1.2 | purchase extra component | Rathanon | 2026-01-21 | 2026-01-30 | 9 | 100% | bar: WEEK 2 W to WEEK 3 F
1.3 | research extra component | Tanakorn | 2026-01-21 | 2026-01-30 | 9 | 100% | bar: WEEK 2 W to WEEK 3 F
1.4 | check requir component | Tanakorn | 2026-01-29 | 2026-02-06 | 7 | 100% | bar: WEEK 3 R to WEEK 4 F
1.5 | test component | Tanakorn | 2026-01-29 | 2026-02-06 | 7 | 100% | bar: WEEK 3 R to WEEK 4 F
1.6 | board assemble | Rathanon | 2026-01-29 | 2026-02-06 | 7 | 100% | bar: WEEK 3 R to WEEK 4 F
2 | Project develope
2.1 | create code | Rathanon | 2026-02-02 | 2026-02-06 | 4 | 100% | bar: WEEK 4 M to WEEK 4 F
2.2 | Budget | Tanakorn | 2026-02-02 | 2026-02-06 | 3 | 100% | bar: WEEK 4 M to WEEK 4 F
2.3 | purchase more component | Tanakorn | 2026-02-06 | 2026-02-12 | 6 | 100% | bar: WEEK 4 F to WEEK 5 R
2.4 | test code | Rathanon | 2026-02-05 | 2026-02-13 | 8 | 100% | bar: WEEK 4 R to WEEK 5 F
3 | Project Finalize and Presentation
3.1 | Final code | Rathanon | 2026-02-16 | 2026-02-19 | 4 | 100% | bar: WEEK 5 W to WEEK 6 R
3.2 | Report summary | Tanakorn | 2026-02-13 | 2026-02-19 | 6 | 100% | bar: WEEK 5 W to WEEK 6 R
3.2.1 | Slide Present | Tanakorn | 2026-02-16 | 2026-02-19 | 4 | 100% | bar: WEEK 6 M to WEEK 6 R
3.2.2 | Project Updates | Rathanon | 2026-02-16 | 2026-02-19 | 4 | 100% | bar: WEEK 6 M to WEEK 6 R
3.3 | Chart Updates | Tanakorn | 2026-02-16 | 2026-02-19 | 4 | 100% | bar: WEEK 6 M to WEEK 6 R
3.3.1 | Presentation | Tanakorn,Rathanon | 2026-02-20 | 2026-02-20 | 1 | 100% | bar: WEEK 6 F